Los Angeles County

# Preface

The 2014 Statewide Medical and Health Functional Exercise is sponsored by the California Department of Public Health (CDPH) and the Emergency Medical Services Authority (EMSA) in collaboration with the California Hospital Association (CHA), California Association of Health Facilities (CAHF), California Primary Care Association (CPCA), the California Office of Emergency Services (Cal OES) and response partners representing local health departments, public safety and health care facilities. This Exercise Plan (ExPlan) was produced with input, advice and assistance from the Statewide and Los Angeles County Medical and Health Exercise Design Workgroup, which followed guidance set forth by the U.S. Department of Homeland Security Exercise and Evaluation Program (HSEEP).

This ExPlan provides officials, observers, media personnel and players from participating organizations the information they need to observe or participate in an exercise focused on medical surge event due to a foodborne disease.  The exercise will test participants’ emergency response plans, policies and procedures as they pertain to an emerging infectious disease. The information in this document is current at the date of publication and is subject to change as dictated by the 2014 Statewide Medical and Health Exercise Design Workgroup and LA County planning team.

# Customizing the Exercise Plan

The ExPlan is a tool for use in planning and conducting the functional exercise. It is designed to be customized by exercise planners for each organization/jurisdiction’s need. Exercise planners may add to either the scenario or Master Scenario Events List (MSEL).

Throughout the ExPlan there are opportunities for customization by organization/jurisdiction planners.  Exercise planners can input their customized language and then remove the highlight.  Some areas may not apply to a jurisdiction/agency/department and can be deleted.  Additional information specific to the jurisdiction may be added by the exercise planner.

# Contents

# Preface..........................................................................................................................  i

# Exercise Overview......................................................................................................  iii

# General Information…………....................................................................................... 1

# Exercise Logistics........................................................................................................ 5

# Post-Exercise and Evaluation Activities.................................................................... 7

Participant Information and Guidance....................................................................... 9

Appendix A: Exercise Schedule..............................................................................  A-1

Appendix B: Exercise Participants.........................................................................  B-1

Appendix C: Communications Plan.......................................................................  C-1

Appendix D: Exercise Site Maps............................................................................  D-1

Appendix E:  Health Alert........................................................................................  E-1

Appendix F:  Acronyms...........................................................................................  F-1

# Exercise Overview

The ExPlan gives elected and appointed officials, observers, media personnel, and players from participating organizations information they need to observe or participate in the exercise.  Some exercise material is intended for the exclusive use of exercise planners, controllers, and evaluators, but players may view other materials that are necessary to their performance.  All exercise participants may view the ExPlan.

| Exercise Name | 2014 California Statewide Medical and Health Functional Exercise |
| --- | --- |
| Exercise Date | November 20, 2014 |
| Scope | This exercise is a [Functional Exercise], planned for November 20th from 9am to 12pm at [exercise location]. The 2014 Statewide Medical and Health Exercise Program is a progressive exercise program in a series of exercises tied to a set of common program priorities. This year’s exercise is a multiphase program designed to be exercised between May and November 2014, culminating in the Functional Exercise on November 20th. Using this approach, each organization/jurisdiction can tailor the exercise to their specific needs. |
| Mission Area(s) | Response and Recovery |
| Core Capabilities | - Operational Communications (Formerly Communications) - Public Health and Medical Services (Formerly Medical Surge and Epidemiological Surveillance and Investigation) - Operational Coordination and On-Site Incident Management (Formerly Emergency Operations Center Management) - Public and Private Services and Resources (Formerly Volunteer Management and Donations) |

| Objectives Objectives | - Assess the communications process internally and externally, based on local policies and procedures. - Review redundant communication modalities within and across response partners. - Determine strengths and weaknesses in activation of medical and health partners surge plans. Identify critical issues and potential solutions. - Identify the process to activate the Incident Command System (ICS) in response to an emerging infectious disease. Determine specific levels necessary based on scenario and local policies and procedures. - Identify the steps in developing an Incident Action Plan (IAP) and conducting associated briefings. - Identify the processes for medical and health partners to provide current situational information to the Medical Health Operational Area Coordinator (MHOAC) Program. - Examine the MHOAC Program’s process to develop and submit a Medical Health Situation Reports consistent with the (EOM). - Identify the process for medical and health partners across the response system to request, distribute, track, and return medical countermeasure resources, including scarce resources, consistent with the EOM. - Validate the processes in place to activate the local disaster medical volunteer system. - Validate the process for epidemiological surveillance information communication and coordination among Medical Health partners, including CDPH, Local Health Department (LHD), Hospitals (specifically between infection prevention, and LHD personnel), and other healthcare facilities. - Identify steps to conduct surveillance and subsequent epidemiological investigations to identify potential exposure and disease. - Examine the process to implement necessary control measures to stop further cases of illness or disease in accordance with established policies. - Identify how the MHOAC Program consolidates and disseminates the epidemiological surveillance information received within the Los Angeles County OA. |
| --- | --- |

| Threat or Hazard | Emerging Infectious Disease |
| --- | --- |
| Scenario | Influenza season has begun and hospitals and primary care see an increase in the number of influenza-like illness (ILI) cases presenting for care including a healthcare worker who returned from the Middle East with symptoms of ILI. The healthcare worker and one of his colleagues test positive for Middle East Respiratory Syndrome - Coronavirus (MERS-CoV). Emergency departments and community health centers see a surge in ILI cases presenting, and admissions increase over 10% with acute respiratory illnesses. |

| Sponsor | The 2014 Statewide Medical and Health Tabletop Exercise is sponsored by CDPH and EMSA in collaboration with CHA, CAHF, CPCA and Cal OES, as well as response partners representing local health departments, public safety and healthcare facilities. |
| --- | --- |
| Participating Organizations | This exercise is designed to include the following medical and health partners: acute care hospitals, local health departments, environmental health departments, community health centers, long term care facilities, dialysis centers, emergency medical services, ambulance providers, law enforcement, fire service, community based organizations, emergency management, MHOAC program, Regional Disaster Medical Health Coordination (RDMHC) program, private physicians, non-governmental organizations, local and state governmental agencies and other response partners. [Please list participating agencies in Appendix B.] |
| Point of Contact | State point of contact: Kristy Perez, Chief, Planning, Exercises and Training Section California Department of Public Health Emergency Preparedness Office 1615 Capitol Avenue MS 7002, Sacramento, CA 95814 Kristy.Perez@cdph.ca.gov Telephone: 916-650-6443 Los Angeles Exercise Co-Chairs: Gary G. Chambers RN BS Disaster Program Manager/TLO Los Angeles County EMS Agency 10100 Pioneer Blvd. Santa Fe Springs, CA 90670 gchambers@dhs.lacounty.gov Office-562.347.1644 Fax-562.944.6931; Ryan Tuchmayer, MPH CEM Disaster Manager Cedars-Sinai Medical Center 8700 Beverly Blvd., TSB 190 Los Angeles, CA 90048 ryan.tuchmayer@cshs.org Office-310.423.4336 Fax-310.423.0143. |

See Appendix F for a listing of agency/event acronyms.

# General Information

## Exercise Objectives and Core Capabilities

The following exercise objectives in Table 1 describe the expected outcomes for the exercise.  The objectives are linked to core capabilities, which are distinct critical elements necessary to achieve the specific mission area(s).  The objectives and aligned core capabilities are guided by issues identified in past exercises and other needs and selected by the Exercise Planning Team.

| Exercise Objective | Core Capability |
| --- | --- |
| - Assess the communications process internally and externally, based on local policies and procedures. | Operational Communications |
| - Review redundant communication modalities within and across response partners. | Operational Communications |
| - Determine strengths and weaknesses in activation of medical and health partners surge plans. Identify critical issues and potential solutions. | Public Health and Medical Services |
| - Identify the process to activate the ICS in response to an emerging infectious disease. Determine specific levels necessary based on scenario and local policies and procedures. | Operational Coordination and On-Site Incident Management |
| - Identify the steps in developing an IAP and conducting associated briefings. | Operational Coordination and On-Site Incident Management |
| - Identify the processes for medical and health partners to provide current situational information to the MHOAC Program | Operational Coordination and On-Site Incident Management |
| - Examine the MHOAC Program’s process to develop and submit a Medical Health Situation Reports consistent with the EOM. | Operational Coordination and On-Site Incident Management |
| - Identify the process for medical and health partners across the response system to request, distribute, track, and return medical countermeasure resources, including scarce resources, consistent with the EOM. | Public and Private Services and Resources |
| - Validate the processes in place to activate the local disaster medical volunteer system. | Public and Private Services and Resources |
| - Validate the process for epidemiological surveillance information communication and coordination among Medical Health partners, including; CDPH, LHD, Hospitals (specifically between infection prevention, and LHD personnel), and other healthcare facilities. | Public Health and Medical Services |
| - Identify steps to conduct surveillance and subsequent epidemiological investigations to identify potential exposure and disease. | Public Health and Medical Services |
| - Examine the process to implement necessary control measures to stop further cases of illness or disease in accordance with established policies. | Public Health and Medical Services |
| - Identify how the MHOAC Program consolidates and disseminates the epidemiological surveillance information received within the Los Angeles County OA. | Public Health and Medical Services |

Table 1. Exercise Objectives and Associated Core Capabilities

## Participant Roles and Responsibilities

The term participant encompasses many groups of people, not just those playing in the exercise.  Groups of participants involved in the exercise, and their respective roles and responsibilities, are as follows:

Players.  Players are personnel who have an active role in performing their regular roles and responsibilities during the exercise.  Players discuss or initiate actions in response to the simulated emergency.

Controllers.  Controllers plan and manage exercise play, set up and operate the exercise site, and act in the roles of organizations or individuals that are not playing in the exercise.  Controllers direct the pace of the exercise, provide key data to players, and may prompt or initiate certain player actions to ensure exercise continuity.  In addition, they issue exercise material to players as required, monitor the exercise timeline, and supervise the safety of all exercise participants.

Simulators.  Simulators are control staff personnel who role play nonparticipating organizations or individuals.  They most often operate out of the Simulation Cell (SimCell), but they may occasionally have face-to-face contact with players.  Simulators function semi-independently under the supervision of SimCell controllers, enacting roles (e.g., media reporters or next of kin) in accordance with instructions provided in the MSEL.  All simulators are ultimately accountable to the Exercise Director and Senior Controller.

Evaluators.  Evaluators evaluate and provide feedback on a designated functional area of the exercise.  Evaluators observe and document performance against established capability targets and critical tasks, in accordance with the Exercise Evaluation Guides (EEGs).

Actors.  Actors simulate specific roles during exercise play, typically victims or other bystanders.  [Delete bullet if not applicable]

Observers.  Observers visit or view selected segments of the exercise.  Observers do not play in the exercise, nor do they perform any control or evaluation functions.  Observers view the exercise from a designated observation area and must remain within the observation area during the exercise.  Very Important Persons (VIPs) are also observers, but they frequently are grouped separately.

Media Personnel.  Some media personnel may be present as observers, pending approval by the sponsor organization and the Exercise Planning Team.  [Delete bullet if not applicable]

Support Staff.  The exercise support staff includes individuals who perform administrative and logistical support tasks during the exercise (e.g., registration, catering).

## Exercise Assumptions and Artificialities

In any exercise, assumptions and artificialities may be necessary to complete play in the time allotted and/or account for logistical limitations.  Exercise participants should accept that assumptions and artificialities are inherent in any exercise, and should not allow these considerations to negatively impact their participation.

### Assumptions

Assumptions constitute the implied factual foundation for the exercise and, as such, are assumed to be present before the exercise starts.  The following assumptions apply to the exercise:

The exercise is conducted in a no-fault learning environment wherein capabilities, plans, systems, and processes will be evaluated.

The exercise scenario is plausible, and events occur as they are presented.

Exercise simulation contains sufficient detail to allow players to react to information and situations as they are presented as if the simulated incident were real.

Participating agencies may need to balance exercise play with real-world emergencies.  Real-world emergencies take priority.

### Artificialities

During this exercise, the following artificialities apply:

[Include any additional simulations to be used in the exercise.]

## Scenario

Influenza season has begun and hospitals and primary care are already seeing an increase in the number of influenza-like illness (ILI) cases presenting for care.

On 11/14/14, a 62 year old male presents to the hospital emergency department (ED) complaining of fever of 102°F, cough, and moderate shortness of breath. During the history and physical, the ED physician obtains key information:

- On 11/12/14, he reported flying back to the California from Germany after a layover.

- On 11/11/14, he traveled by plane to Germany after having worked in Saudia Arabia for six months as a contract health care worker in a hospital located in Jedda. Five other colleagues who had worked with him returned with him on the same flights from Saudi Arabia to Germany and Germany to California.

He is admitted as a suspected MERS case and placed in airborne precautions due to his symptoms and travel history. The physician notifies the local health department (LHD) and specimens are collected for laboratory testing for possible Middle East Respiratory Syndrome – Coronavirus (MERS-CoV), in addition to routine respiratory pathogens, including influenza and other respiratory viruses.

On 11/15/14, two of his colleagues present to separate EDs in the area with worsening symptoms and developing pneumonias.

On 11/17/14, CDPH and CDC laboratories confirm MERS-CoV infection in the 62 year-old male along with one of his fellow healthcare colleagues.

With the confirmation of MERS-CoV, the relatively high incidence of death in other countries, and intense media coverage, people with ILI symptoms are flooding the healthcare system  requesting testing and treatment for MERS-CoV.

EDs and clinics are seeing a definite rise in numbers of ILI cases presenting, and admissions have increased over 10% with acute respiratory illnesses.

On 11/20/14, a group of five people presents to the busy emergency department (ED), with symptoms of ILI.  The group all report two days of fever of 101°F, cough, and increasing mild to moderate shortness of breath.  They state they came to the ED because they recently travelled to Dubai and were concerned after seeing the news coverage of MERS-CoV. Two members of the group had been working as healthcare providers in a Dubai hospital.

# Exercise Logistics

## Safety

Exercise participant safety takes priority over exercise events.  The following general requirements apply to the exercise:

A Safety Controller is responsible for participant safety; any safety concerns must be immediately reported to the Safety Controller.  The Safety Controller and Exercise Director will determine if a real-world emergency, safety concern or disruption warrants a pause in exercise play and when exercise play can be resumed.

For an emergency that requires assistance, use the phrase “real-world emergency.”  The following procedures should be used in case of a real emergency during the exercise:

Anyone who observes a participant who is seriously ill or injured will immediately notify emergency services and the closest controller, and, within reason and training, render aid.

The controller aware of a real emergency will initiate the “real-world emergency” broadcast and provide the Safety Controller, Senior Controller, and Exercise Director with the location of the emergency and resources needed, if any.  The Senior Controller will notify the [Control Cell or SimCell] as soon as possible if a real emergency occurs.

### Weapons Policy [delete section if not applicable]

All participants will follow the relevant weapons policy for the exercising organization or exercise venue.

### Security

If entry control is required for the exercise venue(s), the sponsor organization is responsible for arranging appropriate security measures.  To prevent interruption of the exercise, access to exercise sites and the [Control Cell and/or SimCell] is limited to exercise participants.  Players should advise their venue’s controller or evaluator of any unauthorized persons.

### Media/Observer Coordination [delete section if not applicable]

Organizations with media personnel and/or observers attending the event should coordinate with the sponsor organization for access to the exercise site.  Media/Observers are escorted to designated areas and accompanied by an exercise controller at all times.  Sponsor organization representatives and/or the observer controller may be present to explain exercise conduct and answer questions.  Exercise participants should be advised of media and/or observer presence.

# Post-exercise and Evaluation Activities

## Debriefings

Post-exercise debriefings aim to collect sufficient relevant data to support effective evaluation and improvement planning.

### Hot Wash

At the conclusion of exercise play, controllers facilitate a Hot Wash to allow players to discuss strengths and areas for improvement, and evaluators to seek clarification regarding player actions and decision-making processes.  All participants may attend; however, observers are not encouraged to attend the meeting.  The Hot Wash should not exceed 30 minutes.

### Participant Feedback Forms

Participant Feedback Forms provide players with the opportunity to comment candidly on exercise activities and exercise design.  Participant Feedback Forms should be collected at the conclusion of the Hot Wash.

### Controller and Evaluator Debriefing

Controllers and evaluators attend a facilitated Controller/Evaluator (C/E) Debriefing immediately following the exercise.  During this debriefing, controllers and evaluators provide an overview of their observed functional areas and discuss strengths and areas for improvement.

## Evaluation

### Exercise Evaluation Guides

EEGs assist evaluators in collecting relevant exercise observations.  EEGs document exercise objectives and aligned core capabilities, capability targets, and critical tasks.  Each EEG provides evaluators with information on what they should expect to see demonstrated in their functional area.  The EEGs, coupled with Participant Feedback Forms and Hot Wash notes, are used to evaluate the exercise and compile the After-Action Report (AAR).

### After Action Report

The AAR summarizes key information related to evaluation.  The AAR primarily focuses on the analysis of core capabilities, including capability performance, strengths, and areas for improvement.  It also include basic exercise information, including the exercise name, type of exercise, dates, location, participating organizations, mission area(s), specific threat or hazard, a brief scenario description, and the name of the exercise sponsor and point of contact.

### Improvement Planning

Improvement planning (IP) is the process by which the observations recorded in the AAR are resolved through development of concrete corrective actions, which are prioritized and tracked as a part of a continuous corrective action program.

### After Action Meeting

The After-Action Meeting (AAM) is a meeting held among decision- and policy-makers from the exercising organizations, as well as the Lead Evaluator and members of the Exercise Planning Team, to debrief the exercise and to review and refine the draft AAR and IP.  The AAM should be an interactive session, providing attendees the opportunity to discuss and validate the observations and corrective actions in the draft AAR/IP.

The AAM is scheduled for December 18, 9am-12pm, at the EMS Agency Hearing Room.

### Improvement Plan

The IP identifies specific corrective actions, assigns them to responsible parties, and establishes target dates for their completion.  It is created by elected and appointed officials from the organizations participating in the exercise, and discussed and validated during the AAM.

# Participant Information and Guidance

## Exercise Rules

The following general rules govern exercise play:

Real-world emergency actions take priority over exercise actions.

Exercise players will comply with real-world emergency procedures, unless otherwise directed by the control staff.

All communications (including written, radio, telephone, and e-mail) during the exercise will begin and end with the statement [“This is an exercise.”]

Exercise players who place telephone calls or initiate radio communication with the Simulation Cell (SimCell) must identify the organization or individual with whom they wish to speak.

## Simulation Guidelines

## Because the exercise is of limited duration and scope, certain details will be simulated.  The physical description of what would fully occur at the incident sites and surrounding areas will be relayed to players by simulators or controllers.  A SimCell will simulate the roles and interactions of nonparticipating organizations or individuals.  [Include any additional simulations to be used in the exercise.]

## Players Instructions

Players should follow certain guidelines before, during, and after the exercise to ensure a safe and effective exercise.

### Before the Exercise

Review appropriate organizational plans, procedures, and exercise support documents.

Be at the appropriate site at least thirty minutes before the exercise starts.  Wear the appropriate clothing, uniform and/or identification item(s).

Sign in when you arrive.

If you gain knowledge of the scenario before the exercise, notify a controller so that appropriate actions can be taken to ensure a valid evaluation.

### During the Exercise

Respond to exercise events and information as if the emergency were real, unless otherwise directed by an exercise controller.

Controllers will give you only information they are specifically directed to disseminate.  You are expected to obtain other necessary information through existing emergency information channels.

Do not engage in personal conversations with controllers, evaluators, observers, or media personnel.  If you are asked an exercise-related question, give a short, concise answer.  If you are busy and cannot immediately respond, indicate that, but report back with an answer as soon as possible.

If you do not understand the scope of the exercise, or if you are uncertain about an organization’s participation in an exercise, ask a controller.

Parts of the scenario may seem implausible.  Recognize that the exercise has objectives to satisfy and may require incorporation of unrealistic aspects.  Every effort has been made by the exercise’s trusted agents to balance realism with safety and to create an effective learning and evaluation environment.

All exercise communications will begin and end with the statement [“This is an exercise.”]  This precaution is taken so that anyone who overhears the conversation will not mistake exercise play for a real-world emergency.

When you communicate with the SimCell, identify the organization or individual with whom you wish to speak.

Speak when you take an action.  This procedure will ensure that evaluators are aware of critical actions as they occur.

Maintain a log of your activities.  Many times, this log may include documentation of activities that were missed by a controller or evaluator.

### After the Exercise

Participate in the Hot Wash at your venue with controllers and evaluators.

Complete the Participant Feedback Form.  This form allows you to comment candidly on emergency response activities and exercise effectiveness.  Provide the completed form to a controller or evaluator.

Provide any notes or materials generated from the exercise to your controller or evaluator for review and inclusion in the AAR.

# Appendix A:  Exercise Schedule

[Note:  Because this information is updated throughout the exercise planning process, appendices may be developed as stand-alone documents rather than part of the ExPlan.]

| Time | Personnel | Activity | Location |
| --- | --- | --- | --- |
| [Date] |  |  |  |
| [Time] | Controllers, evaluators, and exercise staff | Controller and Evaluator Briefing | [Location] |
| As needed | Controllers and exercise staff | Set up control cell and walkthrough | [Location] |
| [Date] |  |  |  |
| [Time] | Controllers and exercise staff | Check-in for final instructions and communications check | [Location] |
| [Time] | Media | Media Briefing | [Location] |
| [Time] | VIPs and selected exercise staff | VIP Observer Briefing | [Location] |
| [Time] | Controllers and evaluators | Controllers and evaluators in starting positions | [Location] |
| [Time] | All | Controllers provide player briefs | [Location] |
| 09:00 | All | Exercise starts | [Location] |
| [Time] | All | Exercise ends | [Location] |
| Immediately Following the Exercise | All | Venue Hot Wash/Debrief/turn in all Participant Feedback Forms | [Location] |
| [Date] |  |  |  |
| [Time] | Controllers, evaluators, and elected and appointed officials | Controller and Evaluator After Action Review | [Location] |

# Appendix B:  Exercise Participants

Participating Organizations

# Appendix C:  Communications Plan

[This communication plan below may be utilized or participants may use existing plan.]

All spoken and written communications will start and end with the statement [“This is an exercise.”]

Player Communications

Exercise communications do not interfere with real-world emergency communications.  Players use routine organization communications systems.  Additional communication assets may be made available as the exercise progresses.  Each venue or organization coordinates its internal communication networks and channels.

Controller Communications

The principal methods of information transfer for controllers during the exercise are [landline or cellular telephone, radio, fax, and e-mail].  The controller communications network allows the Exercise Director or Senior Controller to make and announce universal changes in exercise documentation, such as changes to the MSEL.

The primary means of communication among the SimCell, controllers, and Players is [means of communication, e.g., radio (channels), telephone].  A list of key [telephone and fax numbers and radio call signs] will be available before the exercise starts.

Communications Check

Before the exercise, the [Control Cell or SimCell] conducts a communications check with all interfacing communications nodes to ensure redundancy and uninterrupted flow of control information.

Player Briefing

Controllers may be required to provide scenario details to participants to begin exercise play.  Technical handouts or other materials also may be provided to orient players with the exercise.

Public Affairs

The sponsor organization and participating organizations are responsible for coordinating and disseminating public information before the exercise.  Each venue should follow internal procedures.

# Appendix D:  Exercise Site Maps

Figure D.1: [Map Title]

[Insert map]

Figure D.2: [Map Title]

[Insert map

# Appendix E: Health Alert

Health Alert

This is an Exercise Inject for the November 2014 Statewide Medical and Health Exercise ONLY.

MIDDLE EAST RESPIRATORY SYNDROME CORONAVIRUS

Background

In 2012, the World Health Organization (WHO) announced the discovery of a novel coronavirus, MERS-CoV, in Saudi Arabia. Though unrelated to Severe Acute Respiratory Syndrome Coronavirus (SARS-CoV), MERS-CoV is most similar to coronaviruses found in bats.

In November, 2014, cases of MERS-CoV have been identified in counties within California (This is only an Exercise) and also in New York, Florida, and Illinois.

Transmission

The WHO and Centers for Disease Control and Prevention (CDC) have confirmed that there is sustained, widespread human-to-human transmission of MERS-CoV, especially among close contacts (e.g., family members), children younger than 12 years of age, and healthcare workers exposed to cases.

Morbidity and Mortality

Most confirmed cases have had severe acute respiratory illness; some cases have also had gastrointestinal symptoms, including diarrhea.

Complications have included severe pneumonia, acute respiratory distress syndrome (ARDS) with multi-organ failure, renal failure requiring dialysis, consumptive coagulopathy and pericarditis.

The case fatality rate is 40%.  There is no known treatment for MERS-CoV infection; management is supportive.

MERS-CoV Infectious Period

The infectious period for MERS-CoV is likely to extend from the onset of fever until 10-14 days after fever resolves.

MERS-CoV Incubation Period

Current data demonstrates that onset of symptoms has occurred up to 14 days after last exposure.

MERS-CoV Case Definition

Patient Under Investigation (PUI)

A person with the following characteristics should be considered a PUI:

- Fever AND pneumonia or acute respiratory distress syndrome (based on clinical or radiological evidence)

AND EITHER:

  - a history of travel from countries in or near the Arabian Peninsula1 within 14 days before symptom onset, OR

  - close contact2 with a symptomatic traveler who developed fever and acute respiratory illness (not necessarily pneumonia) within 14 days after traveling from countries in or near the Arabian Peninsula1 OR

  - a member of a cluster of patients with severe acute respiratory illness (e.g., fever and pneumonia requiring hospitalization) of unknown etiology in which MERS-CoV is being evaluated, in consultation with state and local health departments.

OR

Fever AND symptoms of respiratory illness (not necessarily pneumonia; e.g. cough, shortness of breath) AND being in a healthcare facility (as a patient, worker, or visitor) within 14 days before symptom onset in a country or territory in or near the Arabian Peninsula in which recent healthcare-associated cases of MERS have been identified3.

- Countries considered in the Arabian Peninsula and neighboring include: Bahrain; Iraq; Iran; Israel, the West Bank, and Gaza; Jordan; Kuwait; Lebanon; Oman; Qatar; Saudi Arabia; Syria; the United Arab Emirates (UAE); and Yemen.

- Close contact is defined as: a)being within approximately 6 feet (2 meters) or within the room or care area for a prolonged period of time (e.g., healthcare personnel, household members) while not wearing recommended personal protective equipment (i.e., gowns, gloves, respirator, eye protection– see Infection Prevention and Control Recommendations; or b) having direct contact with infectious secretions (e.g., being coughed on) while not wearing recommended personal protective equipment (i.e., gowns, gloves, respirator, eye protection – see Infection Prevention and Control Recommendations. Data to inform the definition of close contact are limited. At this time, brief interactions, such as walking by a person, are considered low risk and do not constitute close contact.

- As of June 1, 2014, Jordan, Saudi Arabia, UAE; this may change as more information becomes available.

Confirmed Case

A confirmed case is a person with laboratory confirmation of MERS-CoV infection.

Probable Case

A probable case is a PUI with absent or inconclusive laboratory results for MERS-CoV infection who is a close contact of a laboratory-confirmed MERS-CoV case.

Reference websites on MERS-CoV:

CDPH:  http://www.cdph.ca.gov/programs/cder/Pages/MERS-CoV.aspx

CDC:  http://www.cdc.gov/coronavirus/mers/interim-guidance.html

MERS-CoV Case Reporting

Note:  California Reportable Disease Information Exchange (CalREDIE) will be used for case reporting during the exercise.  The process for this is being developed.  Additional information will be released prior to the exercise about entering cases.

MERS-CoV Specimen Collection and Testing

Polymerase chain reaction (PCR) testing for MERS-CoV is available at the CDPH Viral and Rickettsial Disease Laboratory (VRDL). If this was a real event, local health departments would contact VRDL to arrange shipping of specimens; however, because this is ONLY AN EXERCISE, do not contact VRDL.

Specimen Collection Notes

It is very important that an adequate volume of each specimen type is received by VRDL; without adequate specimen volume incomplete testing will occur and definitive results will be significantly delayed. For this reason, specimens will be prioritized by the local health department for MERS-CoV testing and multiple specimen types as outlined below should be submitted for testing:

- Lower respiratory tract specimens.  Lower respiratory tract specimens typically have the highest yield, i.e., broncheoalveolar lavage, tracheal aspirate, pleural fluid and/or sputum, and should be collected whenever possible and sent in viral transport media (VTM) only; and

- Upper respiratory tract specimens, including nasopharyngeal and oropharyngeal (throat) swabs (nasal washes are not acceptable). Use only synthetic fiber swabs with plastic shafts. Do not use calcium alginate or wooden shaft swabs and send in VTM only; and

- Serum and stool specimens.

Complete the VRDL general purpose specimen submittal form with the specimen(s), available at: http://cdph.ca.gov/programs/vrdl/Pages/CurrentVRDLSpecimenSubmittalforms.aspx

Additional specimen collection information is available at:

http://www.cdc.gov/coronavirus/mers/guidelines-clinical-specimens.html

Isolation Recommendations

Community mitigation and infection control recommendations include isolation of confirmed, probable, or PUI cases.  At this time, quarantine of contacts to confirmed, probable, or PUI cases is not recommended.  However, each Local Health Officer may evaluate the need for quarantine on a case-by-case basis.

Hospitalized Cases: Isolation

Suspect or confirmed cases should be placed in an airborne infection (negative-pressure) isolation room with Airborne, Contact and Standard precautions, including eye protection for healthcare personnel. Isolation should continue until MERS-CoV infection has been ruled out (PCR testing is negative for suspected cases) or until 10 days after resolution of fever in laboratory-confirmed cases.

CDC infection control guidance for MERS-CoV is available at: http://www.cdc.gov/coronavirus/mers/infection-prevention-control.html

Non-Hospitalized Cases:  Home Isolation

Symptomatic persons with suspect or confirmed MERS-CoV infection who are not ill enough to require hospitalization should remain at home in isolation until MERS-CoV infection has been ruled out (PCR testing is negative for suspected cases) or until 10 days after resolution of fever in laboratory-confirmed cases.

Home isolation recommendations include NO movement outside of the home (e.g., isolated person should not go to school, work, child care, community gatherings or other public areas) other than for medical care.

Assess whether the home is suitable and appropriate for isolating the ill person. You can conduct this assessment by phone or direct observation.

- The home should have a functioning bathroom that only the ill person and household members use. If there are multiple bathrooms, one should be designated solely for the ill person.

- The ill person should have his or her own bed and preferably a private room for sleeping.

- Basic amenities, such as heat, electricity, potable and hot water, sewer, and telephone access, should be available.

- If the home is in a multiple-family dwelling, such as an apartment building, the area in which the ill person will stay should use a separate air-ventilation system, if one is present.

- There should be a primary caregiver who can follow the healthcare provider’s instructions for medications and care. The caregiver should help the ill person with basic needs in the home and help with obtaining groceries, prescriptions, and other personal needs.

Additional home care guidelines can be found at http://www.cdc.gov/coronavirus/MERS/hcp/home-care.html.

Isolated persons who must travel outside the home (e.g., doctor visit) should wear a surgical mask and should not use public transportation. Healthcare providers should be notified of suspected or confirmed MERS-CoV infection before the isolated person enters the setting.

Other recommendations for isolated persons include frequent hand washing, covering the mouth and nose when sneezing or coughing, wearing a surgical mask when in the same room as an uninfected person. Isolated persons should not share eating or drinking utensils or towels or bedding with uninfected people.

Household disinfectant or diluted bleach solution (give concentration/dilution instructions) should be used to clean all surfaces contaminated with respiratory sections or other bodily fluids from an isolated person.

Additional information and guidance for community mitigation measures, isolation, and infection control, include:

- Interim Home Care and Isolation Guidance for MERS-CoV at  http://www.cdc.gov/coronavirus/MERS/hcp/home-care.html; and

- Interim Guidance for Preventing MERS-CoV from Spreading in Homes and Communities at http://www.cdc.gov/coronavirus/MERS/hcp/home-care-patient.html

Close Contacts: Self-Monitor

Caregivers, household members, and other people who have had close contact with someone who is being evaluated for MERS-CoV infection should monitor their health for 14 days or until MERS-CoV infection has been ruled out in the contact, starting from the day they were last exposed to the ill person.

Symptom monitoring includes temperature checks twice daily and self-observation for the following respiratory and/or gastrointestinal symptoms:

- Fever (≥ 38°C , 100.4°F)

- Coughing

- Shortness of breath

- Any other symptoms such as chills, body aches, sore throat, headache, diarrhea, nausea/vomiting, and runny nose

If someone who has had close contact with a person being evaluated for MERS-CoV infection develops symptoms, they should alert their local health department immediately and the local health department should arrange for evaluation and testing in a healthcare setting that can provide appropriate isolation and infection control.

While being evaluated, symptomatic contacts should not go to school, work, child care, community gatherings or other public areas other than for medical care. They should also follow other recommendations for persons under home isolation, including wearing a surgical mask when in the same room as an uninfected person, covering the mouth and nose when sneezing or coughing, washing hands frequently, and avoiding sharing household items.

Additional information on MERS-CoV can be found on the CDPH website at http://www.cdph.ca.gov/programs/cder/Pages/MERS-CoV.aspx and the CDC website at http://www.cdc.gov/coronavirus/mers/interim-guidance.html.

Additional MERS-CoV resources can be found at:

- Case Definitions for MERS-CoV:  http://www.cdc.gov/coronavirus/mers/case-def.html

- Interim Guidelines for Specimen Collection and Testing for MERS-CoV:  http://www.cdc.gov/coronavirus/mers/case-def.html

- Interim Infection Prevention and Control Recommendations for Hospitalized Patients with MERS-CoV: http://www.cdc.gov/coronavirus/mers/infection-prevention-control.html

- Interim Home Care and Isolation Guidance for MERS-CoV:  http://www.cdc.gov/coronavirus/mers/hcp/home-care.html

- Frequently Asked Questions and Answers – MERS-CoV:  http://www.cdc.gov/coronavirus/mers/faq.html

This is only an exercise.

November 2014

# Appendix F:  Acronyms

| AAM | After Action Meeting |
| --- | --- |
| AAP | American Academy of Pediatrics |
| AAR | After Action Report |
| AAR/IP | After Action Report/Improvement Plan |
| ARI | Acute Respiratory Infection |
| AST | Ambulance Strike Team |
| ASTL | Ambulance Strike Team Leader |
| BHPP | Building Healthy Public Policy |
| C/E | Controller/Evaluator |
| CAHF | California Association Health Facilities |
| Cal OES | Governor's Office of Emergency Services |
| Cal OSHA | California Division of Occupational Safety and Health |
| CBO | Community Based Organizations |
| CCLHO | California Conference of Local Health Officers |
| CDC | Centers for Disease Control and Prevention |
| CDPH | California Department of Public Health |
| CE | Continuing Education |
| CHA | California Health Association |
| CID | Clinical Infectious Disease |
| CPCA | California Primary Care Association |
| DCDC | Division of Communicable Disease |
| DHS | Department of Homeland Security |
| DOC | Department Operations Center |
| ED | Emergency Department |
| EEGs | Exercise Evaluation Guides |
| EMS | Emergency Medical Services |
| EMSA | Emergency Medical Services Authority |
| EMSC | Emergency Medical Services for Children |
| EOC | Emergency Operation Center |
| EOM | Emergency Operations Manual |
| EPO | Emergency Preparedness Office |
| ExPlan | Exercise Plan |
| FEMA | Federal Emergency Management Agency |
| FTS | Field Treatment Sites |
| GETS | Government Emergency Telecommunications Service |
| HCC | Hospital Command Center |
| HICS | Hospital Incident Command System |
| HSEEP | Homeland Security Exercise and Evaluation Program |
| IAP | Incident Action Plan |
| ICS | Incident Command System |
| ICU | Intensive Care Unit |
| ILI | Influenza-like Illness |
| IP | Improvement Plan |
| JIC | Joint Information Center |
| JIS | Joint Information System |
| LEMSA | Local Emergency Medical Services Authority |
| LHD | Local Health Department |
| MERS-CoV | Middle East Respiratory Syndrome - Coronavirus |
| MHCC | Medical and Health Coordination Center |
| MHOAC | Medical Health Operational Area Coordination Program |
| MRC | Medical Reserve Corps |
| MSEL | Master Scenario Events List |
| NGO | Non-governmental organizations |
| NHICS | Nursing Home Incident Command System |
| NICU | Neonatal Intensive Care Unit |
| NIMS | National Incident Management System |
| OA | Operational Area |
| PAHPRA | Pandemic and All-Hazards Preparedness Reauthorization Act of 2013 |
| POD | Point of Distribution |
| PPE | Personal Protective Equipment |
| RDMHC | Regional Disaster Medical Health Coordination |
| REOC | Regional Emergency Operation Center |
| SEMS | Standardized Emergency Management System |
| SimCell | Simulation Cell |
| SitMan | Situation Manual |
| SME | Subject Matter Expert |
| SOC | State Operational Center |
| UC | Unified Command |
| VIP | Very Important Person |